Government of Saint Lucia

OECS SKILLS FOR INCLUSIVE PROJECT

IDA CREDIT # 4300 - SLU

TERMS OF REFERENCE

for

CONSULTANCY SERVICES TO CONDUCT LABOUR MARKET NEEDS ASSESSMENT

#### August 5, 2011

- Background

According to the Saint Lucia Economic & Social Review 2008, “during 2008 the rapid deterioration of the global economy contributed to the slowdown in the pace of economic activity in Saint Lucia, as was experienced by most CARICOM Countries.”  As a result, more young people are / have become unemployed.  Despite this, there are greater employment opportunities available for youth if they are trained with the right skill sets. In this regard, the Government of Saint Lucia (GOSL) is committed to addressing the urgent need of providing relevant skills for unemployed youth to enter the labor market, as well as opportunities for career advancement. The OECS emphasizes the need to enhance the skills of its citizens and to generate sufficient quality job opportunities to reduce crime and violence among youth and absorb a greater number into the labor force. The GOSL is committed to improving the employability of e unemployed youth and other marginalized sections of the population with the relevant technical and life skills to enter the labor market and build a high quality labor force through training/retraining and enterprise development initiatives. These skills will enable youth to participate in opportunities where there is job demand and reduce their vulnerabilities.

Consequently, the GOSL has secured financing from the World Bank (International Development Association) to implement the OECS Skills for Inclusive Growth Project (the Project), which aims at increasing the employability of youth through demand-driven training by equipping them with the skills, knowledge and attitudes sought by employers. The Project particularly targets disadvantaged youth and focuses on four sectors including Agriculture, Construction, Hospitality and Tourism, and Information Communication Technology (ICT), which had been identified as key economic drivers.

The Project is in line with the GOSL’s Education Development Plan (EDP) for 2006-2010 which places continued emphasis on raising the level of achievement of all learners, reforming the management of education and ensuring certification. With Project support, the GOSL will be able to increase the employability of youth through the establishment of a competitive training scheme that finances private sector-driven training and traineeships and the development of an improved policy framework for delivering training by enhancing OECS collaboration and introducing occupational competency standards to increase quality and value of training.

The Ministry of Education & Culture (MOEC) is responsible for implementation of the Project. The Project is implemented jointly by the Technical and Vocational Education and Training (TVET) Unit of the MOEC, the National Skills Development Centre (NSDC), and the Project Coordination Unit (PCU) of the Ministry of Finance, Economic Affairs and National Development (MOF).

One of the components of the Project is to strengthen the policy framework for delivering training, which includes the development of a Policy Action Plan for Labour Market Needs Assessment. Currently, several government agencies collect data on labor, economic development, tourism revenues, and educational statistics.  Labor reports will discuss employment by sector but specific data drilling down to occupational streams within sectors are lacking. The Labor Market Needs Assessment should serve to analyze the needs and trends of the market place as well as to provide more relevant information on the skill gaps to more effectively anticipate and plan for skills training for youth and to improve the efficiency and effectiveness of technical and vocational training in St Lucia.

- Objectives of the Assignment

The general objective of this assignment is to conduct a Labour Market Needs Assessment in Saint Lucia, which would identify the skills gaps, the anticipated sectors for economic growth, including the targeted sectors, and the specific occupational streams within these sectors. In conducting the assignment, the Consulting Firm is required to assess the employment gaps in St. Lucia in all sectors with emphasis on the four targeted economic sectors (Agriculture, Construction, Hospitality and Tourism, and ICT) and to identify the job opportunities for young persons (ages 16-40) including vulnerable youth. The Labour Market Assessment should provide the GOSL with information on the specific employment patterns in Saint Lucia that would inform future training plans and the formulation of policies and programs for skills training that correspond to the current and projected labor market needs.

The specific objectives of this assignment are:

- To provide efficient, effective and objective consultancy services in identifying the current and future employment gaps in Saint Lucia in all sectors (formal and informal) with emphasis on four main sectors (Agriculture, Construction, Hospitality and Tourism,  and ICT).

- To identify the occupational streams where skilled personnel are needed within the priority sectors based on current and future projections.

- To identify the levels and ranges of specific skills required and to forecast the quality and numbers of skilled persons that need to be trained for wage and self-employment in the occupational streams for the period 2012 – 2017.

- assess the employment trends over the past five years based on workers’ qualifications and job experience and indicate demand for the coming five years;

- identify job opportunities available for the young people (ages 16-40) and other marginalized sections of the population .

- Based on the projected demand, outline occupational streams and levels for which new training programs should be facilitated and areas for further expansion of existing training programs.

- To identify employers’ concerns regarding the deficiencies in the professional profile of applicants, new employees, or new entrants to the labour market and what frame of reference is being used to determine the deficiencies (ie., experience alone or competency standards framework).

- To develop a profile of employees who would meet the expectations of potential employers in the occupational streams of the priority sectors.

- To examine the benefits, risks and challenges for implementing demand-driven skills training in Saint Lucia including the willingness and interest from government, employers, training providers and youth through focus group consultations.

- To provide recommendations or a guide to the government for updating this labor market assessment and how often it should be undertaken.

- Scope of Consultant Services

The Consulting Firm will carry out the following activities, inter alia:

- Be well versed on the current demographic, educational, socio-cultural and economic situation in Saint Lucia through consultation with key informants.

- Based on information collected above, summarize expected economic growth of key sectors in the Saint Lucian economy from existing Government reports for the period 2012-2017 and assess the related employment needs in four priority sectors divided into appropriate sub-sectors.

- In consultation with the Department of Statistics in Saint Lucia, develop a data collection strategy and a survey instrument.  The design of the survey should be based on best practice for labor market needs assessments and be tested and pre-approved by the Government prior to initiating the survey.  This instrument, at a minimum, should request the following types of basic information:

- Type and size of the organization as well as its products and/or services;

- Type and number of persons employed by the organization;

- Wages/salaries for entry-levels;

- Minimum level of education required and preferred for full-time employment;

- Required work experience or certification for employment as an entry-level;

- Degree of difficulty finding qualified personnel;

- Projected number of full-time and part-time job openings and in what occupational streams (2012-17);

- Types of training/skills the organization would like its employees or prospective employees to have (profile); and what training does the employer currently offer if any; Number of vacancies currently unfilled at the firm and the skills, experience and qualifications required to fill these vacancies.

- The importance the employer places on life skills versus technical skills for potential employees at entry level and upper levels.

- Select a representative sample of potential employers proportional to sector size in the economy and establishment size.  Potential employers in all major ISIC (International Standard Industrial Classification) sectors should be selected in consultation with the Department of Statistics for the quantitative study.

- Test data collection instrument (survey) by conducting a pilot test of the survey instrument and process.

- Utilize local survey/data gathering firm to conduct the surveys.

- Supervise survey/data gathering firm to carry out the survey among (500) employers in priority sectors and sub-sectors to:

- Document the expected hires detailed into specific occupations for the next five years. This equally includes surveying employers about the desired skills (technical as well as soft/personal skills) for these hires. Further, the importance of each skill should be rated.

- Receive feedback regarding the ability of the applicants, new employees, or new entrants to the labour market. This should be divided into education level skill level (technical and soft skills), and provide overall comments for improvements.

- Assess the current challenges faced by employers in finding appropriately trained employees.

- Indicate if employers are using competency standards or familiar with the profile of Level One certified persons in their sector.

- Conduct industry-specific focus group discussions with stakeholders that may be comprised of employers, potential trainees, unemployed youth, training providers, appropriate line Ministries (eg., Education, Economic Development, Tourism), NSDC, Labour Department, Statistics Department, National Insurance Corporation, Chamber of Commerce, Sector Associations, and consultants (sector specific resource persons) to collect qualitative data and understand contextual issues.

- Conduct the data analysis and produce the report.

- Outputs

The outputs of the consultancy will comprise:

- Inception Report to include:

- A detailed workplan developed in consultation with officials from the Project Coordination Unit and the Core Team;

A detailed plan for conducting the employers’ survey and analysis of the information generated

- A summary of the findings of the initial meetings conducted with employers and relevant stakeholders;

- A list of relevant information, documents required in order to complete the assignment;

- A set of data collection tools, including the tested survey instrument agreed and cleared with the Government

- Electronic copy of raw data collected

- Reports from stakeholder consultations

- Final reports to include:

- Identification of existing and projected skill gaps for the period 2012-2017, including identification of occupation streams within priority sectors with the highest demand for new employees and related skills;

- Identification of skill sets and a profile of employees who would meet the expectations of potential employers in the occupation streams identified above;

- Identification of key challenges currently faced by employers in finding the required skills, and recommendations for addressing these challenges;

- Recommendations on future skill training to be offered in Saint Lucia, including the skill areas to be expanded, the options to stimulate and sustain greater investment in training by employers and individuals, or any other issues which would contribute to more relevant and responsive training provision in Saint Lucia; and

- Assessment of capacity to deliver the proposed training, including the identification of the required training equipment and facilities, and the availability of qualified and experienced training providers (public and private).

All reports shall be submitted in English. Draft copies of reports may be submitted by electronic mail. An electronic copy and three hard copies of the Final Report formatted in Microsoft Word/Excel shall be submitted.

The Consulting Firm shall ensure the timely submission of these outputs to the Project Steering Committee for review. The Committee will ensure the timely review and acceptance of the reports, not more than two (2) weeks after the receipt of the reports from the Consulting Firm.

All reports and documents relevant to this Consultancy including field survey notes, computer programmes, etc. shall become the property of the Government of Saint Lucia.

- Responsibilities of the Consulting Firm

In conducting the assignment, the Consulting Firm is expected to:

- Utilize individual interviews, focus group discussions and a structured survey of employers, as the main techniques in carrying out this assignment.

- Collect both quantitative and qualitative data, and reflect this duality in both the findings and recommendations.

- Conduct activities in close collaboration with employers, government officials, officials from training institutions/firms, relevant trade associations, and youth, drawing from their experiences and obtaining information from them. Conduct meetings with them as well as other stakeholders to develop the activities.

- Collect, study and use all data necessary to ensure that activities are in keeping with policies, and plans at local, regional and sub-regional levels and is consistent with research findings and developments worldwide.

- Select the appropriate mix of stakeholders for focus group sessions to inform the qualitative analysis.

- Ensure that the ILO standards for the conduct of this analysis are observed in the data processing and analysis.

- Supervise the data collection/survey firm to ensure quality standards and methodology is adhered to.

- Implementation and Working Arrangements

The Consulting Firm shall include a Lead Investigator/Researcher for the Labor Market Needs Assessment.  The Lead Researcher will oversee and manage the activities of this assignment and will assume full responsibility for timely delivery of the expected outputs of the assignment, as listed in Section 4: Outputs.

The consultancy services will be implemented under the OECS Skills for Inclusive Growth Project of the GOSL through the Project Coordination Unit.  The Consulting Firm will work directly with the PCU, MOF. The Project Coordinator, PCU with the assistance of the Director of the Statistics Department of the GOSL is responsible for supervising the assignment. Supervisory responsibilities of the PCU and the Director of Statistics include: (i) liaising with the Consulting Firm; (ii) clarification of assigned tasks; (iii) assisting in organization of consultations; and (iv) reporting on completion of assigned tasks.

- Timeframe

The anticipated time required for completion of the consultancy is five (5) months, commencing November 1, 2011 and continuing through April 1, 2012, as per the attached work schedule.

| Period | Activities |
| --- | --- |
| Month 1 | - Familiarization with the demographic, educational, socio-cultural and economic situation in Saint Lucia. - Presentation of the inception report and finalization of a detailed work plan in agreement with the Client. - Consultations with stakeholders - Draft of survey instrument – review with Govt stakeholders. |
| Month 2 | - Testing and finalization of the survey instrument. - Supervising local survey firm to carry out data collection, implementation of surveys with approximately 500 employers. |
| Month 3 | - Continue supervising survey work. - Analyze results of survey information. |
| Month 4 | - Drafting of the survey analysis and labor market assessment report |
| Month 5 | - Briefings to the stakeholder institutions and World Bank staff on the main findings - Finalization of the report |

An Inception Report shall be submitted to the PCU, MOF within one week of the commencement of the consultancy.  The Client shall submit comments within one week of receipt of the report.

A Draft Final Report shall be submitted to the PCU, MOF. The Client shall submit comments within two weeks of receipt of this report.

- Qualifications / Experience

The Consulting Firm shall have experts with the following or equivalent qualifications and experience:

Lead Researcher

- At least a Masters Degree, preferably within the field of economics or related field. A specialization in labour economics would be an asset,

- At least 5-7 years of labor market research and analysis.

Statistician

- At least a Masters Degree in Statistics or a related field,

- At least 3 years experience in data analysis.

The firm in general:

- Experience in developing and implementing labor market needs assessments. It is preferable if the firm has working experience in the Organization of Eastern Caribbean States (OECS) or the wider Caribbean.

- Experience in using survey software is desirable,

- Excellent interpersonal communication skills, and demonstrated ability to work and collaborate with a wide range of local and international partner organizations,

- Ability to work independently and to manage multiple tasks,

- Fluency in English; excellent writing skills.

- Schedule of Payments

- 10%  of the Contract Sum upon signing of the Contract Document

- 10% of the Contract Sum upon submission of the Inception Report, acceptable to the Client

- 15% of the Contract Sum upon completion and testing of the survey instrument, acceptable to the Client;

- 40% of the Contract Sum upon submission of the Draft Survey analysis and labor market assessment Report, acceptable to the Client;

- 25% of the Contract Sum upon submission of the Final Report, acceptable to the Client

The raw data, data analysis and final report will be the property of the Government of Saint Lucia at the completion of the assignment.

The target is the young people between the ages of 16 and 40, who have passed less than 4 CXC exams or with only Standard Six School Leaving Certificate.

The training scheme requires training in technical areas that are in demand in the marketplace. The scheme includes a combination of life skills training + technical training + a traineeship/apprenticeship with an employer.