SAINT LUCIA: OECS SKILLS FOR INCLUSIVE GROWTH PROJECT

IDA CREDIT #4300-SLU

CONSULTANCY

Labour Market Needs Assessment

The Government of Saint Lucia (GOSL) represented by the Ministry of Finance, Economic Affairs and National Development seeks to hire a Consulting Firm to provide Consulting Services to Conduct a Labour Market Needs Assessment.

Expressions of Interests are invited are invited from suitably qualified Consulting Firms to provide consulting services to the Saint Lucia OECS Skills for Inclusive Growth Project.

Objectives

The general objective of this assignment is to conduct a Labour Market Needs Assessment in Saint Lucia, which would identify the skills gaps, the anticipated sectors for economic growth, including the targeted sectors, and the specific occupational streams within these sectors. In conducting the assignment, the Consulting Firm is required to assess the employment gaps in St. Lucia in all sectors with emphasis on the four targeted economic sectors (Agriculture, Construction, Hospitality and Tourism, and ICT) and to identify the job opportunities for young persons (ages 16-40) including vulnerable youth. The Labour Market Assessment should provide the GOSL with information on the specific employment patterns in Saint Lucia that would inform future training plans and the formulation of policies and programs for skills training that correspond to the current and projected labor market needs.

Scope of Services

The Consulting Firm will carry out the following activities, inter alia:

- Be well versed on the current demographic, educational, socio-cultural and economic situation in Saint Lucia through consultation with key informants.

- Based on information collected above, summarize expected economic growth of key sectors in the Saint Lucian economy from existing Government reports for the period 2012-2017 and assess the related employment needs in four priority sectors divided into appropriate sub-sectors.

- In consultation with the Department of Statistics in Saint Lucia, develop a data collection strategy and a survey instrument.  The design of the survey should be based on best practice for labor market needs assessments and be tested and pre-approved by the Government prior to initiating the survey.  This instrument, at a minimum, should request the following types of basic information:

- Type and size of the organization as well as its products and/or services;

- Type and number of persons employed by the organization;

- Wages/salaries for entry-levels;

- Minimum level of education required and preferred for full-time employment;

- Required work experience or certification for employment as an entry-level;

- Degree of difficulty finding qualified personnel;

- Projected number of full-time and part-time job openings and in what occupational streams (2012-17);

- Types of training/skills the organization would like its employees or prospective employees to have (profile); and what training does the employer currently offer if any; Number of vacancies currently unfilled at the firm and the skills, experience and qualifications required to fill these vacancies.

- The importance the employer places on life skills versus technical skills for potential employees at entry level and upper levels.

- Select a representative sample of potential employers proportional to sector size in the economy and establishment size.  Potential employers in all major ISIC (International Standard Industrial Classification) sectors should be selected in consultation with the Department of Statistics for the quantitative study.

- Test data collection instrument (survey) by conducting a pilot test of the survey instrument and process.

- Utilize local survey/data gathering firm to conduct the surveys.

- Supervise survey/data gathering firm to carry out the survey among (500) employers in priority sectors and sub-sectors to:

- Document the expected hires detailed into specific occupations for the next five years. This equally includes surveying employers about the desired skills (technical as well as soft/personal skills) for these hires. Further, the importance of each skill should be rated.

- Receive feedback regarding the ability of the applicants, new employees, or new entrants to the labour market. This should be divided into education level skill level (technical and soft skills), and provide overall comments for improvements.

- Assess the current challenges faced by employers in finding appropriately trained employees.

- Indicate if employers are using competency standards or familiar with the profile of Level One certified persons in their sector.

- Conduct industry-specific focus group discussions with stakeholders that may be comprised of employers, potential trainees, unemployed youth, training providers, appropriate line Ministries (eg., Education, Economic Development, Tourism), NSDC, Labour Department, Statistics Department, National Insurance Corporation, Chamber of Commerce, Sector Associations, and consultants (sector specific resource persons) to collect qualitative data and understand contextual issues.

- Conduct the data analysis and produce the report.

Duration

The anticipated time required for completion of the consultancy is five (5) months, commencing November 1, 2011 and continuing through April 1, 2012.

Qualifications and Skills Requirements

The Consulting Firm shall have experts with the following or equivalent qualifications and experience:

Lead Researcher

- At least a Masters Degree, preferably within the field of economics or related field. A specialization in labour economics would be an asset,

- At least 5-7 years of labor market research and analysis.

Statistician

- At least a Masters Degree in Statistics or a related field,

- At least 3 years experience in data analysis.

The firm in general:

- Experience in developing and implementing labor market needs assessments. It is preferable if the firm has working experience in the Organization of Eastern Caribbean States (OECS) or the wider Caribbean.

- Experience in using survey software is desirable,

- Excellent interpersonal communication skills, and demonstrated ability to work and collaborate with a wide range of local and international partner organizations,

- Ability to work independently and to manage multiple tasks,

- Fluency in English; excellent writing skills.

Further information on the assignment is contained in the Terms of Reference which can be obtained from the Project Coordination Unit.

Expressions of Interests should be submitted to the:

The Project Coordinator

Project Coordination Unit

Ministry of Finance, Economic Affairs and National Development

2nd Floor, American Drywall Building

Vide Boutielle, Castries

Saint Lucia

Email: slupcu@gosl.gov.lc

Fax Number: 758-453-0417

To reach no later than September 16, 2011

Interested persons may contact the Project Coordination Unit at Telephone

# 468-5816/5820 for more information on the Terms of Reference

Selection will be done in accordance with the IBRD/IDA Guidelines for Selection of Consultants